## Product Overview
Attribute | Value
Product Name | ValBot
Target Users | Visitors, Buyers, Sellers, Admins
AI Model | GPT-4o-mini (primary), text-embedding-3-small
Knowledge Source | FAQs, Help Center, Policies, Documentation
Core Capability | Listing search via natural language + RAG Q&A
Memory | Session (visitor) / Persistent 90 days (logged-in)
Response Style | Streaming, concise, action-oriented
Platform | Web widget embedded in ValClassifieds SPA
Architecture | Conversation Manager → AI Orchestrator → OpenAI
Key Components | PromptBuilder, ContextBuilder, ToolRouter, PermissionChecker, ResponseValidator, CostTracker, AnalyticsLogger
Estimated Dev | ~54 days over 7 weeks (Phase 1A: 17d, Phase 1B: 17d)
Estimated Monthly Cost | ~$303 at 500K messages
Target Satisfaction | >85% thumbs-up rate

## MVP Definition
Phase | Feature | Priority | Dependencies
Phase 1A | Chat widget UI (floating launcher, panel, conversation UI) | P0 | None
Phase 1A | Session management (visitor + logged-in) | P0 | Auth provider
Phase 1A | Conversation persistence (DB + API contract) | P0 | Supabase project
Phase 1A | Streaming response infrastructure (SSE scaffolding) | P0 | None
Phase 1A | Authentication awareness (role detection) | P0 | Auth provider
Phase 1A | Error handling + loading states + typing indicator | P0 | UI components
Phase 1A | Unit & integration tests for UI layer | P0 | Test framework
Phase 1B | OpenAI integration (adapter + streaming) | P0 | OpenAI API key
Phase 1B | AI Orchestrator (PromptBuilder, ContextBuilder, ToolRouter, PermissionChecker) | P0 | Phase 1A
Phase 1B | RAG pipeline (embedding + vector search + reranking) | P0 | Supabase pgvector
Phase 1B | Response Validator (guardrails, hallucination check, PII filter) | P0 | Phase 1B orchestrator
Phase 1B | Cost Tracker + Analytics Logger | P0 | Phase 1B orchestrator
Phase 1B | Conversation Manager + token budget | P0 | Phase 1B API
Phase 2 | System prompt engineering + tool definitions | P0 | Phase 1B
Phase 2 | Listing cards + suggested replies | P1 | Phase 1A UI
Phase 2 | Conversation memory (cross-session) | P1 | Phase 1B
Phase 2 | Escalation to human | P1 | Phase 1B
Phase 3 | Rate limiting (hard enforcement) | P2 | Phase 2
Phase 3 | Admin monitoring dashboard | P2 | Phase 1B DB
Phase 3 | Analytics pipeline | P2 | Phase 1B

## Intent Library
ID | Intent Name | Description | Example | Priority | Requires Auth
INT-01 | GREETING | User greets the chatbot | Hi, Hello, Hey | P0 | No
INT-02 | MARKETPLACE_INFO | What is ValClassifieds? | How does it work? | P0 | No
INT-03 | CATEGORY_BROWSE | Browse categories | What categories? | P0 | No
INT-04 | CATEGORY_HELP | Ask about a category | Tell me about electronics | P0 | No
INT-05 | SEARCH_LISTING | Find listings | Show phones under 20K | P0 | No
INT-06 | LISTING_DETAIL | Listing details | Tell me about listing #123 | P0 | No
INT-07 | SELLER_INFO | Seller info | Who is selling this? | P0 | No
INT-08 | COMPARE_LISTINGS | Compare items | Compare these two | P1 | No
INT-09 | BUYING_HELP | How to buy | How do I buy? | P0 | No
INT-10 | SELLING_HELP | How to sell | How do I sell? | P0 | No
INT-11 | LISTING_TIPS | Listing optimization | Best photos? | P1 | No
INT-12 | PRICING_HELP | Pricing guidance | How much to charge? | P1 | No
INT-13 | PROMOTION_INFO | Promoted listings | What are featured? | P1 | No
INT-14 | FAQ_QUESTION | FAQ questions | Is it free? | P0 | No
INT-15 | POLICY_QUESTION | Policy questions | Refund policy? | P0 | No
INT-16 | SAFETY_INFO | Safety info | How to avoid scams? | P0 | No
INT-17 | ACCOUNT_HELP | Account assistance | Reset password? | P0 | Yes
INT-18 | SEARCH_REFINE | Refine search | Under 20K, In Hyderabad | P0 | No
INT-19 | ESCALATE | Human support | Talk to a human | P1 | No
INT-20 | FEEDBACK | User feedback | That was helpful | P0 | No
INT-23 | FALLBACK | Unrecognized query | (any) | P0 | No

## Role Matrix
Capability | Visitor | Buyer | Seller | Admin | Notes
Browse categories | ✅ | ✅ | ✅ | ✅
Search listings | ✅ | ✅ | ✅ | ✅
View listing details | ✅ | ✅ | ✅ | ✅
View seller info | ✅ | ✅ | ✅ | ✅ | Public info only
FAQ / Policy answers | ✅ | ✅ | ✅ | ✅
Buying guidance | ✅ | ✅ | ✅ | ✅ | Basic version
Selling guidance | ❌ | ❌ | ✅ | ✅ | Requires seller login
Pricing suggestions | ❌ | ❌ | ✅ | ✅
Listing promotion info | ❌ | ❌ | ✅ | ✅
Account help | ❌ | ✅ | ✅ | ✅ | Requires login
Conversation history | ❌ | ✅ | ✅ | ✅
Feedback submission | ✅ | ✅ | ✅ | ✅
Escalation to human | ✅ | ✅ | ✅ | ✅
Admin dashboard | ❌ | ❌ | ❌ | ✅
Browse all conversations | ❌ | ❌ | ❌ | ✅
Knowledge base management | ❌ | ❌ | ❌ | ✅
View analytics | ❌ | ❌ | ❌ | ✅

## Success Metrics & KPIs
KPI | Definition | Target | Measurement
Conversation Success Rate | No escalation or negative feedback | >80% | feedback + escalation analysis
Resolution Rate | Queries answered without escalation | >90% | escalation analysis
Fallback Rate | Unrecognized queries (INT-23) | <10% | Intent classification logs
P50 Response Latency | Median time to first token | <1.5s | Server-side timing
P95 Response Latency | 95th percentile response time | <4s | Server-side timing
Avg Tokens per Response | Mean tokens per assistant message | <500 | chatbot_messages.tokens
Monthly Cost | Total OpenAI + infra cost | <$500 | Billing dashboard
User Satisfaction | Thumbs-up rate | >85% | chatbot_feedback.rating
User Retention | Return for 2nd conv within 7 days | >30% | chatbot_conversations
Listing Click-Through | Listing card clicks / views | >15% | Analytics events
Escalation Rate | Conversations that escalate | <5% | chatbot_escalations
Avg Conversation Length | Mean messages per conversation | 4-8 | chatbot_messages

## Release Roadmap
Phase | Weeks | Key Deliverables | Effort | Go/No-Go Gate
Phase 1A: UI & Infrastructure | 1-2 | Chat widget, session mgmt, DB schema, SSE scaffolding, tests | 17 days | Chat widget renders, sends messages, receives mock SSE, persists convs
Phase 1B: AI Engine | 2-3 | OpenAI adapter, AI Orchestrator, RAG, ResponseValidator, CostTracker | 17 days | End-to-end AI conversation with streaming, RAG, and tools
Phase 2: Core Experience | 3-4 | Prompt engineering, tool definitions, listing cards, suggested replies, conversation memory | 14 days | Full conversation flow with search, RAG, suggestions
Phase 3: Production Hardening | 5-6 | Rate limiting, error handling, admin dashboard, analytics, escalation | 14 days | All tests pass, security review complete
Phase 4: Launch | 7 | Performance opt, cost monitoring, gradual rollout, docs | 8 days | All KPIs green at 5% traffic for 48h
Phase 5: Post-Launch | 8+ | Feedback analysis, KB expansion, multi-language, voice input | Ongoing | Continuous improvement

## Tool Specifications
Tool | Description | Allowed Roles | Parameters | Output | Timeout | Retry | Rate Limit
searchListings | Natural language listing search | All roles | query, category, minPrice, maxPrice, location, condition, sort, limit | Listing[] (max 5) | 5s | 1 @ 1s | 10/conv
getListingDetail | Single listing details | All roles | listingId (UUID) | Full listing object | 3s | 1 @ 500ms | 20/conv
getCategories | All available categories | All roles | None | Category[] (all 16) | 2s | None (cache) | 5/conv
getSellerInfo | Public seller profile | All roles | sellerId (UUID) | Public profile (no contact) | 3s | 1 @ 500ms | 15/conv
getPolicies | Policy/FAQ information | All roles | topic (string) | Policy text + sources | 3s | 1 retry | 10/conv
escalateToHuman | Escalate to support agent | All roles | reason (string) | Escalation ID + ticket | 3s | 1 retry | 3/conv
adminGetConversation | Browse any conversation | Admin only | conversationId (UUID) | Full conversation | 3s | 1 retry | 30/conv
adminGetAnalytics | Retrieve analytics | Admin only | metric, period | Aggregated data | 3s | 1 retry | 30/conv
adminUpdateKnowledge | Upload/re-index KB | Admin only | sourceType, content | Confirmation + chunk count | 5s | 1 retry | 10/conv

## Prompt Library
Template | Purpose | Key Sections | Variables
System Prompt (Base) | Instructions for AI behavior | Identity, Core Rules, User Context, RAG Context, Tools, Tone | role, full_name, member_since, current_page, rag_context
Greeting (Returning) | Welcome back message | Welcome message, last context summary, options | last_context_summary
Search Response | Format listing search results | Count, category, cards, follow-up options | count, category, query, listing_cards
Policy Response | Format policy answer | Answer, source citation, follow-up | policy_answer, source_name
Seller Guidance | Selling tips and advice | Tips for topic, related topics | topic, tip_1/2/3, related_topic_1/2
Buyer Guidance | Buying help and search results | Results, tip, refinement options | query, listing_cards, buying_tip
Visitor Welcome | First-time visitor greeting | Feature highlights, action options | None (static)
Admin Greeting | Admin login summary | Name, summary stats, review options | name, count, rate, escalations
Fallback | Unrecognized query | Apology, help options | None (static)
Refusal (4 variants) | Out-of-scope decline | Polite decline, redirection | None (static)
Escalation | Human handoff | Confirmation, ticket info, summary | ticket_id, contact_method, response_time, conversation_summary

## Test Strategy
Test Suite | Scope | Test Cases | Automation
Functional Tests | Widget, messages, SSE, conversations, feedback, errors | ~60 | Playwright
Conversation Tests | Happy paths, edge cases, multi-turn, context, roles, escalation | ~68 | Playwright + Manual
Security Tests | API key exposure, JWT, rate limits, prompt injection (20 cases), RLS, PII | ~64 | Automated + Manual
Performance Tests | Load (100 users), stress (500), endurance (1h), spike (10x), latency | 5 scenarios | k6
Prompt Validation | Relevance, out-of-scope, hallucination, tone, refusal quality | Weekly review | Manual + Auto
Hallucination Tests | Non-existent policies, listing counts, competitor queries | ~8 | Automated
RAG Accuracy Tests | FAQ retrieval, policy matching, ambiguous queries, empty results | ~10 | Automated

## Response Types
Type | Description | Rendering | Example Use Case
text | Plain markdown text | Text bubble with markdown support | Simple informational reply
listing_card | Single listing result | Card with image, price badge, link | Show one listing detail
category_card | Category information | Card with icon, count, browse link | Category browsing help
seller_card | Seller public profile | Card with avatar, stats, profile link | Seller info display
policy_card | Policy or FAQ content | Card with Q&A and source citation | Policy explanations
faq_card | FAQ accordion item | Expandable Q&A with feedback prompt | FAQ lookups
carousel | Horizontal scrollable cards | Swipeable/paginated card set | Multiple listing results
pagination | Pagination control | "Showing X-Y of Z" + Load More | More results available
warning | Notice banner | Colored banner with action button | Non-critical notices
error | Error message | Error banner with retry button | Operation failure
escalation | Human handoff | Confirmation card with ticket info | Escalation created
typing | Animated typing indicator | Animated dots + contextual label | Waiting for response
loading | Progress indicator | Skeleton/placeholder | Multi-step operations
empty_state | No results found | Icon + message + suggestions + actions | Empty search results