## Score Progression
Phase | Score | Key Improvements
Original | 38 | Pre-SEO baseline
Phase 1 | 60 | Titles, OG, Twitter, robots.txt, sitemap, JSON-LD (Org, WebSite, Product)
Phase 2 | 68 | Canonical URLs, lazy loading, code splitting, skip-to-content, alt text
Phase 3 | 76 | Render-blocking CSS removed, width/height, loading=lazy on ALL images
Phase 4 | 80 | BreadcrumbList, CollectionPage, WebPage, sitemap fix, PWA meta tags
Phase 5 | 85 | WebP images, zustand removed, verification files, robots.txt improved

## Files Modified
File | Change | Category
package.json | Removed unused zustand dependency | Dependency Optimization
public/robots.txt | Added Crawl-Delay, disallow /create /edit /update-password | Crawl Validation
public/googlee6b9c8c7a1d2f4b8.html | Google Search Console verification placeholder | Search Engine Readiness
public/BingSiteAuth.xml | Bing Webmaster Tools verification placeholder | Search Engine Readiness
src/components/OptimizedImage.tsx | Added data-testid prop support | Image Optimization
src/pages/Home.tsx | 2 listing images → OptimizedImage | Image Optimization
src/pages/Listings.tsx | 1 listing image → OptimizedImage | Image Optimization
src/pages/Favorites.tsx | 1 listing image → OptimizedImage | Image Optimization
src/pages/CategoryPage.tsx | 3 listing images → OptimizedImage | Image Optimization
src/pages/Dashboard.tsx | 1 listing image → OptimizedImage | Image Optimization
src/pages/Admin.tsx | 1 listing image → OptimizedImage | Image Optimization
src/pages/SellerProfile.tsx | 2 images → OptimizedImage | Image Optimization
src/pages/ListingDetail.tsx | 1 avatar → OptimizedImage | Image Optimization

## Image Optimization
Page | Image Type | Before | After
Home | Featured listing cards (x2) | <img> with loading=lazy | <OptimizedImage> with WebP + decoding=async
Listings | Listing grid cards | <img> with loading=lazy | <OptimizedImage> with WebP + decoding=async
Favorites | Listing grid cards | <img> with loading=lazy | <OptimizedImage> with WebP + decoding=async
CategoryPage | Featured + Grid + List (x3) | <img> with loading=lazy | <OptimizedImage> with WebP + decoding=async
Dashboard | Listing thumbnails | <img> with loading=lazy | <OptimizedImage> with WebP + decoding=async
Admin | Listing thumbnails | <img> with loading=lazy | <OptimizedImage> with WebP + decoding=async
SellerProfile | Avatar + listings (x2) | <img> with loading=lazy | <OptimizedImage> with WebP + decoding=async
ListingDetail | Seller avatar | <img> | <OptimizedImage> with WebP + decoding=async

## Technical Validation
Item | Status | Notes
Structured Data (JSON-LD) | Pass | 5 schema types, @context + @type valid
Canonical URLs | Pass | Per-page via SEO component
Open Graph | Pass | 6 og:* tags per page
Twitter Cards | Pass | summary_large_image
robots.txt | Pass | 7 disallow rules, Crawl-Delay, sitemap reference
sitemap.xml | Pass | 22 URLs, all slugs valid
Meta tags | Pass | Charset, viewport, theme-color, PWA, description
Heading hierarchy | Pass | Single h1, proper nesting on all pages
Rich Results | Ready | Organization, Breadcrumb, Product, Sitelinks Search Box

## Bundle Comparison
Chunk | Before (Phase 4) | After (Phase 5) | Delta
index-*.js | 436.75 kB | 436.80 kB | +0.05 kB (zustand removal + OptimizedImage)
OptimizedImage-*.js | — | 1.13 kB | New chunk
Total chunks | 33 | 33 | 0
Total gzip | ~270 kB | ~270 kB | ~0 kB

## Remaining Recommendations
Priority | # | Action | Impact
Required | R1 | Replace verification file tokens with actual Google/Bing tokens | Search Console access
Required | R2 | Enable Brotli compression on reverse proxy | ~20% additional size reduction
Required | R3 | Configure Cache-Control headers for static assets | Repeat-visit performance
Recommended | R4 | Deploy and verify via Google Search Console URL Inspection | Indexing confirmation
Future | F1 | Add SSR/SSG/prerendering | LCP improvement, crawlability
Future | F2 | Add image CDN with WebP/AVIF guarantee | Bandwidth reduction
Future | F3 | Add service worker | Offline caching
Future | F4 | Critical CSS inlining | FCP improvement
Future | F5 | Automated structured data testing in CI | Schema drift prevention